## Sheet1
Unit ID | New Status | Revised Finish Date | Notes
REN-001 | Awaiting Inspection | 2025-08-05 | Drywall and painting complete. Inspector scheduled for Aug 5.
REN-003 | In Progress | 2025-09-10 | Electrical rough-in started. Running 2 weeks behind schedule.
REN-004 | Completed | 2025-08-02 | All work signed off. Ready for tenant move-in.
REN-006 | In Progress | 2025-09-15 | Demolition complete. Framing underway.
REN-007 | Awaiting Inspection | 2025-08-18 | Plumbing and fixtures installed. Awaiting city sign-off.
REN-009 | In Progress | 2025-10-15 | Permit issue resolved. Restarting work next week.
REN-010 | Completed | 2025-09-18 | Final walkthrough passed. Unit ready.
REN-012 | Awaiting Inspection | 2025-08-28 | All trades done. Punch list items cleared.
REN-015 | In Progress | 2025-10-20 | Structural assessment complete. Work resuming.
REN-016 | Completed | 2025-09-25 | Kitchen and bathrooms finished. Passed inspection.
REN-018 | Awaiting Inspection | 2025-08-22 | Ready for final inspection. Minor touch-ups done.
REN-020 | In Progress | 2025-09-15 | Tile work delayed due to material backorder.