## Master Tracker
Unit ID | Property Address | Status | Original Finish Date | Revised Finish Date
REN-001 | 142 Maple Street Unit 1A | In Progress | 2025-07-15 | 2025-08-01
REN-002 | 142 Maple Street Unit 1B | Completed | 2025-06-30 | 2025-06-30
REN-003 | 142 Maple Street Unit 2A | Pending | 2025-08-20 | 2025-08-20
REN-004 | 78 Oak Avenue Unit 3 | In Progress | 2025-07-28 | 2025-09-05
REN-005 | 78 Oak Avenue Unit 4 | Awaiting Inspection | 2025-07-10 | 2025-07-22
REN-006 | 301 Birch Boulevard Apt 6 | Pending | 2025-09-01 | 2025-09-01
REN-007 | 301 Birch Boulevard Apt 7 | In Progress | 2025-08-05 | 2025-08-15
REN-008 | 55 Cedar Lane Unit 8 | Completed | 2025-06-15 | 2025-06-15
REN-009 | 55 Cedar Lane Unit 9 | On Hold | 2025-07-20 | 2025-10-01
REN-010 | 200 Elm Drive Suite 10 | In Progress | 2025-08-12 | 2025-09-20
REN-011 | 200 Elm Drive Suite 11 | Pending | 2025-09-10 | 2025-09-10
REN-012 | 410 Pine Road Unit 12 | In Progress | 2025-07-25 | 2025-08-30
REN-013 | 410 Pine Road Unit 13 | Awaiting Inspection | 2025-07-05 | 2025-07-18
REN-014 | 88 Walnut Court Apt 14 | Completed | 2025-06-20 | 2025-06-20
REN-015 | 88 Walnut Court Apt 15 | On Hold | 2025-08-01 | 2025-11-15
REN-016 | 500 Spruce Way Unit 16 | In Progress | 2025-08-22 | 2025-09-30
REN-017 | 500 Spruce Way Unit 17 | Pending | 2025-09-15 | 2025-09-15
REN-018 | 77 Willow Lane Unit 18 | In Progress | 2025-07-30 | 2025-08-20
REN-019 | 77 Willow Lane Unit 19 | Awaiting Inspection | 2025-07-12 | 2025-07-25
REN-020 | 33 Aspen Close Unit 20 | In Progress | 2025-08-08 | 2025-09-12